## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
TASK-LIST
| Table 1 | TASK-LIST
Queries
| Table 1 | Queries
DATA
| Table 1 | DATA

## TASK-LIST
Table 1
PHASE | DATE | DAYS | HOURS | TASK | SUBTASK | DETAIL | TEAM | STATUS | OWNER | NOTES
Project Setup | 2026-01-19 | 2.5 | 6 | Backend Setup | Generate Quarkus project |  | BACKEND | Open
|  |  | 4 |  | Configure Docker Compose |  | BACKEND | Open
|  |  | 6 | Frontend Setup | Initialize Vite + React + TypeScript project |  | UI | Open
|  |  | 4 |  | Set up React Router, API client (Axios/Fetch), state management |  | UI | Open
Authentication & User Management | 2026-01-21 | 13 | 6 | Quarkus Security + JWT | Configure Quarkus JWT |  | BACKEND
|  |  | 7 |  | Implement UserService for authentication |  | BACKEND
|  |  | 4 |  | Create JWT token generation and validation |  | BACKEND
|  |  | 6 |  | Build RBAC annotations |  | BACKEND
|  |  | 6 |  | Create authentication endpoints |  | BACKEND
|  |  | 8 |  | Integrate with Clerk |  | BACKEND
|  |  | 16 | Login & Session Management | Build React login page |  | UI
|  |  | 6 |  | Integrate with Clerk |  | UI
|  |  | 6 |  | Role-based routing in React |  | UI
|  |  | 7 | Clinician Registration Flow | Account creation API |  | BACKEND
|  |  | 8 |  | Account creation Page |  | UI
|  |  | 5 |  | Email Verification Service
|  |  | 7 | Provider Registration Flow | Facility account creation API | Pending verification state Admin approval workflow | BACKEND
|  |  | 8 |  | Facility account creation Page |  | UI
|  |  | 4 |  | Admin Approval Workflow
Provider Experience | 2026-02-03 | 34 | 8 | Provider Dashboard | Build ProviderStats Service |  | BACKEND | Open
|  |  | 8 |  | Create REST endpoint for ProviderStats Service | Analytic Data API | BACKEND | Open
|  |  | 16 |  | Build React dashboard with stat cards and bed availability widget |  | UI | Open
|  |  | 8 |  | Recent activity feed component |  | BACKEND | Open
|  |  | 6 |  | Review Service - API |  | BACKEND
|  |  | 8 |  | React page for review response |  | UI
|  |  | 6 |  | Service to upload image |  | BACKEND
|  |  | 8 |  | React page to upload image |  | UI
|  |  | 8 | Bed Availability Management | Create BedAvailability Service with CRUD operations | POST, GET, UPDATE METHODS | BACKEND | Open
|  |  | 6 |  | Bed availability history log |  | BACKEND | Open
|  |  | 6 |  | Status calculation logic |  | BACKEND | Open
|  |  | 16 |  | React bed management UI with +/- buttons |  | UI | Open
|  |  | 8 | Magic Link System | Create cron job |  | BACKEND
|  |  | 10 |  | Create MagicLink Service |  | BACKEND
|  |  | 6 |  | Build BedUpdateToken entity and repository |  | BACKEND
|  |  | 8 |  | Implement token expiration logic |  | BACKEND
|  |  | 6 |  | Quarkus Scheduler for daily magic link delivery (cron expression) |  | BACKEND
|  |  | 6 |  | SMS integration for magic link delivery |  | BACKEND
|  |  | 6 |  | Email integration for magic link delivery |  | BACKEND
|  |  | 7 |  | IP logging and audit trail |  | BACKEND
|  |  | 16 |  | React public magic link update page |  | UI
|  |  | 8 | Profile Management | Build ProviderProfileService (CRUD operations) |  | BACKEND
|  |  | 8 |  | Geocoding API wrapper Service |  | BACKEND
|  |  | 14 |  | Geocoding API integration (address autocomplete) |  | UI
|  |  | 7 |  | Profile completion calculation |  | BACKEND
|  |  | 24 |  | React profile editor form with multi-select components |  | UI
|  |  | 6 | Provider Settings | Create ProviderSettings and service | Get Account Setting API Update Account Setting API | BACKEND
|  |  | 12 |  | Notification preferences and rest endpoint |  | BACKEND
|  |  | 16 |  | React settings page |  | UI
Clinician Experience | 2026-03-03 | 38 | 8 | Clinician Dashboard | Recently viewed providers Service |  | BACKEND
|  |  | 7 |  | Saved searches service |  | BACKEND
|  |  | 12 |  | Notifications API |  | BACKEND
|  |  | 6 |  | React notification highlighter
|  |  | 16 |  | Activity API |  | BACKEND
|  |  | 16 |  | Dashboard page creation and integration |  | UI
|  |  | 8 | Search Implementation | Implement hybrid search service API |  | BACKEND
|  |  | 7 |  | Multi-filter logic (insurance, level of care, demographics) |  | BACKEND
|  |  | 6 |  | Faceted search (filter counts) |  | BACKEND
|  |  | 8 |  | REST search endpoint with pagination (GET /search) |  | BACKEND
|  |  | 8 | Search Results & Map | Build React search results page layout |  | UI
|  |  | 7 |  | Advanced filter sidebar with collapsible sections |  | UI
|  |  | 10 |  | Provider result cards with bed availability display |  | UI
|  |  | 7 | Provider Detail | Create ProviderDetailDTO with all profile data |  | BACKEND
|  |  | 6 |  | REST endpoint |  | BACKEND
|  |  | 7 |  | Profile view tracking |  | UI
|  |  | 10 |  | React provider detail page with hero section |  | UI
|  |  | 12 |  | Tabbed content (Overview, Insurance, Contact, Reviews, Details) |  | BACKEND
|  |  | 14 |  | Map embed showing facility location |  | UI
|  |  | 8 | Saved Facilities | Create SavedProviderService and entity |  | BACKEND
|  |  | 6 |  | REST endpoints (POST/DELETE /saved-providers, GET /saved-providers) |  | BACKEND
|  |  | 6 |  | Tags system (create, filter by tags) |  | BACKEND
|  |  | 8 |  | Personal notes (per facility) |  | BACKEND
|  |  | 8 |  | React saved facilities page with search/filter |  | UI
|  |  | 7 | Contact Log System | Create ContactLogService and entity |  | BACKEND
|  |  | 8 |  | REST endpoints (POST/GET/PUT /contact-logs) |  | BACKEND
|  |  | 12 |  | Stats calculation (today, this week, this month) |  | BACKEND
|  |  | 10 |  | Follow-up reminder system (scheduled notifications) |  | BACKEND
|  |  | 10 |  | React contact log page with timeline view |  | UI
|  |  | 6 | Review & Rating System | Create ReviewService and entity |  | BACKEND
|  |  | 6 |  | REST endpoints (POST/GET /reviews) |  | BACKEND
|  |  | 10 |  | Average rating calculation and update on provider |  | BACKEND
|  |  | 12 |  | React review submission form |  | UI
|  |  | 12 |  | Review list display on provider detail page |  | UI
Admin Experience | 2026-04-01 | 34 | 12 | Admin Dashboard | Create AdminStatsService (platform metrics) |  | Backend | Open
|  |  | 16 |  | REST endpoint (GET /admin/stats) |  | Backend | Open
|  |  | 16 |  | Summary Report API |  | Backend | Open
|  |  | 14 |  | React admin dashboard with key metrics cards |  | UI | Open
|  |  | 16 |  | React admin dashboard with graphs
|  |  | 8 | Provider Management | Create Provider Service with different status |  | Backend | Open
|  |  | 10 |  | REST endpoints with pagination |  | Backend | Open
|  |  | 10 |  | Email notifications on approval/rejection |  | Backend | Open
|  |  | 12 |  | Verification audit log |  | Backend | Open
|  |  | 8 |  | React verification queue with filterable table |  | UI
|  |  | 8 |  | React provider cards
|  |  | 12 |  | React Filter section
|  |  | 10 | User Management | Create UserManagementService (CRUD operations) |  | Backend | Open
|  |  | 8 |  | REST endpoints (GET/PUT /admin/users) |  | Backend | Open
|  |  | 12 |  | User Data Export API |  | Backend | Open
|  |  | 16 |  | React user management table with search/filters |  | UI | Open
|  |  | 16 | Analytics | Create AnalyticsService (search logs, user growth queries) | Summary Report API Search Report API User Report API Analytic Data API | Backend | Open
|  |  | 10 |  | REST endpoints (GET /admin/analytics) |  | Backend | Open
|  |  | 16 |  | Analytics page and integration |  | UI | Open
|  |  | 16 |  | React admin dashboard with graphs
|  |  | 8 | Review Moderation(Pending Action Section) | Create Moderation Service (approve/reject/hide reviews) |  | Backend | Open
|  |  | 8 |  | REST endpoints (GET/PUT /admin/reviews) |  | UI | Open
|  |  | 10 |  | React moderation queue |  | UI
| 2026-04-29 |  |  |  | LIVE |  |  | Open

## Queries
Table 1
1 | Billing section is missing
2 | Subscription and Billing detail
3 | External verification integration (recovery.com or LegitScript)
4 | History Log has to be maintain?
5 | Full Manager action is unknown - Provider Dashboard
6 | Profile Visibility - Public, private and verified
7 | While showing the Provider data to clinician, we have more fields than taking data from the provider

## DATA
Table 1
Web / Mobile Frontend
¦
v
Quarkus API (Monolith-first, modular)
¦
├── Auth & Users
├── Clinician Search (PostGIS)
├── Provider Management
├── Reviews & Ratings
├── Admin & Moderation
¦
PostgreSQL + PostGIS
| Factor | Node.js | Java + Quarkus | Winner
| PostGIS integration | ✅ | ✅ (JDBC, Hibernate, Panache) | Tie
| Radius search only | ✅ | ✅ | Tie
| High concurrency | ⚠️ | ✅ | Quarkus
| CPU headroom | ❌ | ✅ | Quarkus
| Type safety | ⚠️ | ✅ | Quarkus
| Enterprise readiness | ⚠️ | ✅ | Quarkus
| Kubernetes / EKS | ⚠️ | ✅ | Quarkus
| Native startup | ❌ | ✅ | Quarkus
| Long-term maintainability | ⚠️ | ✅ | Quarkus