## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
TASK-LIST
| Table 1 | TASK-LIST
Queries
| Table 1 | Queries
DATA
| Table 1 | DATA

## TASK-LIST
Table 1
PHASE | DATE | TASK | SUBTASK | DETAIL | TEAM | STATUS | OWNER | NOTES
Authentication & User Management | 2026-01-19 | Authentication | Universal Login API | JWT issuance & refresh, Password hashing and policy,Session expiration rules, Logout & token revocation, Google sign in, Forgot password | Backend | Open
| 2026-01-20 |  | Sign Up API |  | Backend | Open
|  |  | Login page | Design login page | UI | Open
| 2026-01-21 | Clinician Registration Flow | Account creation API |  | Backend | Open
|  |  | Account creation Page | Include 3 steps | UI | Open
|  |  | Email Verification Service |  |  | Open
| 2026-01-23 | Provider Registration Flow | Facility account creation API |  | Backend | Open
|  |  | Facility account creation Page |  | UI | Open
|  |  | External verification integration (Recovery.com or LegitScript) |  | Backend | Open |  | Need more detail on it
|  |  | Pending verification state |  | Backend | Open
|  |  | Admin approval workflow |  | Backend | Open |  | Manually approving initially
Clinician Experience | 2026-01-28 | Clinician Dashboard | Recently viewed providers API |  | Backend | Open
|  |  | Saved searches API |  | Backend | Open
|  |  | Notifications API |  | Backend | Open
|  |  | Activity API |  | Backend | Open
|  |  | Dashboard page creation and integration |  | UI | Open
| 2026-02-02 | Search Results | Search API | Filter handling Sorting logic Search validation Search Entry (Dashboard) Location input (geo / autocomplete), Pagination | Backend | Open
|  |  | Save Search API |  | Backend | Open
|  |  | Save facilities API |  | Backend | Open
|  |  | Get Saved Search API |  | Backend | Open
| 2026-02-05 |  | Search Page creation and integration |  | UI | Open
[5 empty] | Backend | Open
| 2026-02-09 | Provider Detail | View Search Result API |  | Backend | Open
|  |  | Search Result Page creation and integration |  | UI | Open
| 2026-02-11 | Submit Review | Submit Review API |  | Backend | Open
|  |  | Submit Review page creation and integration |  | UI | Open
| 2026-02-16 | Saved Facilities | Get Saved Facilities API |  | Backend | Open
|  |  | Saved Facilities page creation and integration |  | UI | Open
| 2026-02-19 | Contact Log | Get contact Log API |  | Backend | Open
|  |  | Create new contact log API |  | Backend | Open
|  |  | Update contact log API |  | Backend | Open
|  |  | Contact Log page creation and integration |  | UI | Open
Provider Experience | 2026-02-24 | Provider Dashboard | Analytic Data API |  | Backend | Open
|  |  | Get Bed Availability API |  | Backend | Open
|  |  | Update Bed Availability API |  | Backend | Open
|  |  | Update/Edit Profile API |  | Backend | Open
|  |  | Get Profile API |  | Backend | Open
|  |  | Activity API |  | Backend | Open
|  |  | Review API |  | Backend | Open
|  |  | Update Review API |  | Backend | Open
| 2026-02-27 |  | Dashboard page creation and integration |  | UI | Open
| 2026-03-03 | Edit Profile | Save Profile API |  | Backend | Open
| 2026-03-05 |  | Profile page creation and integration |  | UI | Open
| 2026-03-10 | Provider Setting | Get Account Setting API |  | Backend | Open
|  |  | Update Account Setting API |  | Backend | Open
|  |  | Subscription and Billing |  | Backend | Open |  | Subscription and Billing are we planning this too now
| 2026-03-13 |  | Account Setting page creation and integration |  | UI | Open
| 2026-03-18 |  | Magic Link Provider API(for Scheduled delivery- cron job) |  | Backend | Open
| 2026-03-23 |  | UI Page to update beds |  | UI | Open
| 2026-03-25 |  | Testing
Admin Experience | 2026-03-26 | Admin Dashboard | Recent Activity API |  | Backend | Open
|  |  | Pending Action API |  | Backend | Open
|  |  | Summary Report API |  | Backend | Open
| 2026-03-31 |  | Dashboard page creation and integration |  | UI | Open
| 2026-04-06 | Provider Management | Summary Report for Provider API |  | Backend | Open
|  |  | Get All Provider API - Pagination |  | Backend | Open
|  |  | Search with Filter for Provider API |  | Backend | Open
| 2026-04-10 |  | Provider Management page creation and integration |  | UI | Open
| 2026-04-15 | User Management | Summary Report for User API |  | Backend | Open
|  |  | Get All user detail API - Pagination |  | Backend | Open
|  |  | User Data Export API |  | Backend | Open
|  |  | Add New user API |  | Backend | Open
|  |  | User Management page creation and integration |  | UI | Open
| 2026-04-20 | Analytics | Summary Report API |  | Backend | Open
|  |  | Search Report API |  | Backend | Open
|  |  | User Report API |  | Backend | Open
|  |  | Analytic Data API |  | Backend | Open
|  |  | Analytics page and integration |  | UI | Open
| 2026-04-27 |  | LIVE |  |  | Open

## Queries
Table 1
1 | Billing section is missing
2 | Subscription and Billing detail
3 | External verification integration (recovery.com or LegitScript)
4 | History Log has to be maintain?
5

## DATA
Table 1
Web / Mobile Frontend
¦
v
Quarkus API (Monolith-first, modular)
¦
├── Auth & Users
├── Clinician Search (PostGIS)
├── Provider Management
├── Reviews & Ratings
├── Admin & Moderation
¦
PostgreSQL + PostGIS
| Factor | Node.js | Java + Quarkus | Winner
| PostGIS integration | ✅ | ✅ (JDBC, Hibernate, Panache) | Tie
| Radius search only | ✅ | ✅ | Tie
| High concurrency | ⚠️ | ✅ | Quarkus
| CPU headroom | ❌ | ✅ | Quarkus
| Type safety | ⚠️ | ✅ | Quarkus
| Enterprise readiness | ⚠️ | ✅ | Quarkus
| Kubernetes / EKS | ⚠️ | ✅ | Quarkus
| Native startup | ❌ | ✅ | Quarkus
| Long-term maintainability | ⚠️ | ✅ | Quarkus